## Slide 1: Project Health Portfolio Review
Executive synthesis for client leadership

## Slide 2: Portfolio Health
Portfolio health: 0 Green, 0 Amber, 2 Red

## Slide 3: Trend Snapshot
2 project(s) are Red, 0 are Amber, and 0 are Green
Schedule slippage is the dominant cross-project risk

## Slide 4: Risk Trends
Dependencies: 263FS +1d, 292, 293FS +2d, 332, 395, 421, 447
Dependencies: 3FS +7d, 8FF, 16FS +6d
Risks logged: Due to parallel phase 1 activities onsite workshop dates are impacted
Schedule is slipping by 8 days
Schedule is slipping by 81 days
Zycus - UniSan S2P Implementation

## Slide 5: Delayed Milestones
Go Live (61d behind)
Load delta master data via integration (63d behind)
P2P Cutover (62d behind)
Phase 2 - P2P (81d behind)
Review SOW with UniSan (8d behind)

## Slide 6: Emerging Risks
No material updates to report.

## Slide 7: Recommendations
Escalate the delivery risk and agree on a recovery plan within 48 hours

## Slide 8: Next Month Outlook
Stabilize schedule-critical workstreams and remove blockers before the next steering review